## WBS
WBS ID (Unique ID within this spreadsheet) | Unique # in Jira (if any) | Epic Improvement New Feature Task Bug | Complexity S - < 8 Hrs M - 8 -16 Hrs L - 16 -32 Hrs XL - 32 - 40 Hrs | Functionality | Work Description | Dependency to Start (Provide the WBS ID of the line dependent on) | Dependency to Finish (Provide the WBS ID of the line dependent on) | Sprint | Planned Start Date | Planned End Date | Resource | Current Status
1 | TDEB-2 | Epic |  | App Connect | AppConnect Application
2 | TDEB-6 | New Feature |  | App Connect | API to Handle Talkdesk Uninstall Events |  |  | Sprint 1 | 2019-06-27 | 2019-07-02 | Dhipak | Done
3 | TDEB-5 | New Feature |  | App Connect | API to Handle Talkdesk Updated Event |  |  | Sprint 1 | 2019-06-27 | 2019-07-02 | Dhipak | Done
4 | TDEB-4 | New Feature |  | App Connect | API to Handle Talkdesk Install Events |  |  | Sprint 1 | 2019-06-27 | 2019-07-02 | Vijay | Done
5 | TDEB-3 | New Feature |  | App Connect | Mock - Consume Event Signature |  |  | Sprint 1 | 2019-07-01 | 2019-07-04 | Anand | Done
6 | TDEB-37 | New Feature |  | App Connect | API to store and access app credentials |  |  | Sprint 1 | 2019-07-01 | 2019-07-03 | Sagitya | Done
| TDEB-62 | Task |  | App Connect | Apply App Connect install link in TD instance |  |  | Sprint 1 | 2019-07-09 | 2019-07-10 | Phillip
7 | TDEB-7 | New Feature |  | App Connect | Integrate with Talkdesk SSO |  | New-1 | Sprint 1 | 2019-07-10 | 2019-07-12 | Anand/Phillip
8 | TDEB-38 | New Feature |  | App Connect | Integrate with Talkdesk events |  | New-1 | Sprint 1 | 2019-07-10 | 2019-07-12 | Anand/Phillip
| TDEB-71 | Task |  | App Connect | Create Users when instal event happens |  |  | Sprint 1 | 2019-07-10 | 2019-07-12 | Anand/Sahitya
| TDEB-72 | Task |  | App Connect | During the uninstall event make the account inactive and update the client id and client secret fields as null. |  |  | Sprint 2 |  |  | Anand
9 | TDEB-12 | Epic |  | Campaign Mgmt | Customer Facing API to Create Manage Campaigns and Campaign Lines
10 | TDEB-39 | Task |  | Campaign Mgmt | API - Create campaign (post) |  |  | Sprint 1 | 2019-07-04 | 2019-07-10 | Vijay | WIP
11 | TDEB-40 | Task |  | Campaign Mgmt | API - Create campaign lines (post) |  |  | Sprint 1 | 2019-07-04 | 2019-07-09 | Sagitya | WIP
12 | TDEB-41 | Task |  | Campaign Mgmt | API - Report outcome details by Campaign id, candidate id and by status |  |  | Sprint 2 | 2019-07-03 | 2019-07-05 | Dhipak
13 | TDEB-42 | Task |  | Campaign Mgmt | API - Create campaign template |  |  | Sprint 1 | 2019-07-04 | 2019-07-09 | Dhipak | WIP
| TDEB-43 | Task |  | Campaign Mgmt | API - Report Campaign summary for requested campaign status like Open/In Progress/Closed |  |  | sprint 2
| TDEB-44 | Task |  | Campaign Mgmt | API - Update Campaign. Not available for Campaigns in progress and closed |  |  | Sprint 2 |  |  | Vijay
| TDEB-45 | Task |  | Campaign Mgmt | API - Update Campaign lines. Not available for Campaigns in progress and closed |  |  | Cancel
| TDEB-46 | Task |  | Campaign Mgmt | API - Cancel Campaign (not applicable for in-progress and closed) |  |  | Sprint 2 |  |  | Vijay
| TDEB-47 | Task |  | Campaign Mgmt | API - Close Campaign (not applicable for in-progress and closed) |  |  | Discuss |  |  |  |  | To be done using GUI
| TDEB-48 | Task |  | Campaign Mgmt | When the campaign is in progress, No further changes should be allowed to be made in the campaign other than the call results. Also, the time-stamp of each campaign when started and completed should be available for reporting |  |  | Discuss
| TDEB-49 | Task |  | Campaign Mgmt | When the camapaign gets completed, a notification should be sent to the requestor on the status. |  |  | Sprint 2
| TDEB-75 | Task |  | Campaign Mgmt | Related to TDEB-49. Outbound Request to be generated
14 | TDEB-33 | Task |  | Architecture | Application and Deployment architecture - Arrive at the optimum sizing and also finalize the infra components
15 | TDEB-34 | Task |  | Architecture | Architecture diagram |  |  | Sprint 1 | 2019-07-01 | 2019-07-11 | Vinoth | In-progress
| TDEB-63 | Task |  | Architecture | Create Develoopment Environment for Build |  |  | Sprint 1 | 2019-07-08 | 2019-07-09 | Dhipak | WIP
16 | TDEB-35 | Task |  | Architecture | Identify OAuth node package and do quick poc whether its fit for purpose |  |  | Sprint 1 | 2019-07-04 | 2019-07-04 | Parthiban & Karthik | Done
17 | TDEB-31 | Epic |  | Call Scheduler | Campaign Start: Call Distribution
18 | TDEB-36 | Task |  | Call Scheduler | Analysis and Design of Call distribution |  |  | Sprint 1 | 2019-06-24 | 2019-07-14 | Vinoth | In-progress
19 | TDEB-50 | Task |  | Call Scheduler | Code distribution algorithm |  |  | Sprint 1 | 2019-07-04 | 2019-07-11 | parthiban | WIP
20 | TDEB-51 | Task |  | Call Scheduler | Review of distribution algorithm |  |  | Sprint 2
21 | TDEB-52 | Task |  | Call Scheduler | Develop code to pick data from campaign lines and populate batch table |  |  | Sprint 1 | 2019-07-08 | 2019-07-10 | parthiban/Vijay
22 | TDEB-53 | Task |  | Call Scheduler | Develop code to process data from Batch and update campaigns/lines |  |  | Sprint 1 | 2019-07-08 | 2019-07-10 | Anand/Dheepauk | WIP
| TDEB-73 | Task |  | Service Level | Call report to be fetched from TD instance |  |  | Sprint 2 |  |  | Un assigned
| TDEB-74 | Task |  | Service Level | Process the call report |  |  | Sprint 2 |  |  | Un assigned
24 | TDEB-13 | Epic |  | Call Scheduler | Talkdesk Campaign Services
25 | TDEB-54 | New Feature |  | Call Scheduler | Integrate scheduler, Presence and call distribution services |  |  | Sprint 2
26 | TDEB-32 | Epic |  | Call Scheduler | Agent Presence Logic
27 | TDEB-55 | Task |  | Call Scheduler | Analysis of Presence API and Decide on the approach |  |  | Sprint 1 | 2019-07-04 | 2019-07-10 | Anand/Phillip
28 | TDEB-56 | Task |  | Call Scheduler | Create Code get all agents status and store in db |  |  | Sprint 2
29 | TDEB-57 | Task |  | Call Scheduler | Create code get aggregation of available status of agent |  |  | Sprint 2
30 | TDEB-58 | Task |  | Call Scheduler | Create api to read the no of agents available status |  |  | Sprint 2
| TDEB-64 | Task |  | Call Scheduler | Check API Presence access in TD instance |  |  | Sprint 1 | 2019-07-08 | 2019-07-08 | Phillip | Discuss
31 | TDEB-1 | Epic |  | Campaign Mgmt- UI | Utilize the Talkdesk Cobalt UI Framework with the Talkdesk EB App.
32 | TDEB-21 | Task |  | Campaign Mgmt- UI | Edit Campaign Line Page for Cobalt |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip | Review
33 | TDEB-20 | Task |  | Campaign Mgmt- UI | Edit Campaign Page for Cobalt |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip | Review
34 | TDEB-19 | Task |  | Campaign Mgmt- UI | Campaign Line Page for Cobalt |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip | Review
35 | TDEB-18 | Task |  | Campaign Mgmt- UI | Campaign Page for Cobalt |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip | Review
36 | TDEB-17 | Task |  | Campaign Mgmt- UI | Convert Campaign Dashboard for Cobalt |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip | Review
37 | TDEB-16 | Task |  | Campaign Mgmt- UI | Implement Talkdesk Dock with Drawer |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
38 | TDEB-11 |  |  | Campaign Mgmt- UI | The Process for Creating and Maintaining Campaigns
39 | TDEB-23 | Task |  | Campaign Mgmt- UI | Edit Talkdesk Campaign Lines |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
40 | TDEB-22 | Task |  | Campaign Mgmt- UI | Edit a Talkdesk Campaign |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
41 | TDEB-10 | Task |  | Campaign Mgmt - UI | Create Talkdesk Campaign Lines |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
42 | TDEB-9 | Task |  | Campaign Mgmt- UI | Create a Talkdesk Campaign |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
43 | TDEB-8 | Task |  | Campaign Mgmt | Ability to Mass Import Campaign Lines Using a CSV File |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
44 | TDEB-24 | Task |  | Campaign Management | As a user I would like buttons to control a campaign |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
45 | TDEB-27 | Task |  | Camapaign Management | Campaign Pause Service |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
46 | TDEB-26 | Task |  | Camapaign Managmnt | Campaign Stop Service |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
47 | TDEB-25 | Task |  | Camapaign Managtmtnt | Campaign Start Service |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
48 | TDEB-59 | Task |  | Campaign Management | Add tenant_id to all tables and refer in GUI |  |  | Sprint 1 | 2019-07-01 | 2019-07-12 | Phillip
49 | TDEB-15 | Epic |  | User Administration | OAuth 2 for Partner and Third Party Integrations
50 | TDEB-28 | Task |  | User Administration | As a Partner, I would like to request for a Client ID and Secret |  |  | Sprint 1 | 2019-07-01 | 2019-07-02 | Parthiban | Done
51 | TDEB-30 | Task |  | User Administration | As a Partner, I should be able to use a refresh token to request a new access token if the one currently in use expires |  |  | Discuss
52 | TDEB-29 | Task |  | User Administration | As a Partner, I should be able to request an access token using my Client ID and Secret |  |  | Sprint 1 | 2019-07-01 | 2019-07-02 | Parthiban | Done
| TDEB-65 | Epic |  | Release Mgmt | Release Management
| TDEB-66 | Task |  | Release Mgmt | 1st Deployment to Heroku from Hibiz Repositoryy |  |  | Sprint 1 | 2019-07-11 | 2019-07-12 | Anand/Phillip
| TDEB-69 | Task |  | Retrofits | Code Refactoring for Integration |  |  | Sprint 2
53 | TDEB-60 | Epic |  | Testing | Functional Integration Testing
| TDEB-67 | Task |  | Testing | Functional Integration Testing (Iteration 1) |  |  | Sprint-2
| TDEB-68 | Task |  | Testing | Functional Integration Testing (Iteration 2) |  |  | Sprint 3
54 | TDEB-61 | Task |  | Testing | Performance Testing |  |  | Discuss
| TDEB-70 | Epic |  | Retrofits | Code Refactoring for Integration
56 | TDEB-69 | Task |  | Retrofits | Code Refactoring for - TBD |  |  | .Sprint-2
| TDEB-76 | Epic |  |  | SMS Campaign
| TDEB-77 | Task |  |  | SMS with Tivilio - Design
| TDEB-78 | Task |  |  | SMS with other Careers - Design
| TDEB-79 | Task |  |  | SMS with Tivilio - Dev
| TDEB-80 | Task |  |  | SMS with other Careers - Dev
| TDEB-81 | Epic |  |  | App Settings
| TDEB-82 | Task |  |  | Settings - GUI
| TDEB-83 | Task |  |  | Settings - Schema
| TDEB-84 | Epic |  |  | Logger
| TDEB-85 | Task |  |  | Construct Logger for Campaign and Campaign lines
| TDEB-86 | Task |  |  | Construct Logger for events
| TDEB-87 | Task |  |  | Construct Logger for Call Distribution

## Sprint
| Start Date | End Date
Sprint 1 | 2019-07-01 | 2019-07-12
Sprint 2 | 2019-07-15 | 2019-07-26
Sprint 3 | 2019-07-29 | 2019-08-09