## WBS
WBS ID (Unique ID within this spreadsheet) | Unique # in Jira (if any) | Epic Improvement New Feature Task Bug | Complexity S - < 8 Hrs M - 8 -16 Hrs L - 16 -32 Hrs XL - 32 - 40 Hrs | Functionality | Work Description | Dependency to Start (Provide the WBS ID of the line dependent on) | Dependency to Finish (Provide the WBS ID of the line dependent on) | Sprint | Planned Start Date | Planned End Date | Resource | Current Status | Sprints
1 | TDEB-2 | Epic |  | App Connect | AppConnect Application
2 | TDEB-6 | New Feature |  | App Connect | API to Handle Talkdesk Uninstall Events |  |  |  | 2019-06-27 | 2019-07-02 | Dhipak | In-progress
3 | TDEB-5 | New Feature |  | App Connect | API to Handle Talkdesk Updated Event |  |  |  | 2019-06-27 | 2019-07-02 | Dhipak | In-progress
4 | TDEB-4 | New Feature |  | App Connect | API to Handle Talkdesk Install Events |  |  |  | 2019-06-27 | 2019-07-02 | Vijay | In-progress
5 | TDEB-3 | New Feature |  | App Connect | Mock - Consume Event Signature |  |  |  | 2019-07-01 | 2019-07-04 | Anand
6 | New | New Feature |  | App Connect | API to store and access app credentials |  |  |  | 2019-07-01 | 2019-07-03 | Sagitya | In-progress
7 | TDEB-7 | New Feature |  | App Connect | Integrate with Talkdesk SSO
8 | New | New Feature |  | App Connect | Integrate with Talkdesk events
9 | TDEB-12 | Epic |  | Campaign Mgmt | Customer Facing API to Create Manage Campaigns and Campaign Lines
10 | New | New Feature |  | Campaign Mgmt | API - Create campaign (post) |  |  |  | 2019-07-03 | 2019-07-05 | Vijay
11 | New | New Feature |  | Campaign Mgmt | API - Create campaign lines (post) |  |  |  | 2019-07-04 | 2019-07-05 | Sagitya
12 | New | New Feature |  | Campaign Mgmt | API - Report outcome details by Campaign id, candidate id and by status |  |  |  | 2019-07-03 | 2019-07-05 | Dhipak
13 | New | New Feature |  | Campaign Mgmt | API - Create campaign template
| New | New Feature |  | Campaign Mgmt | API - Report Campaign summary for requested campaign status like Open/In Progress/Closed
| New | New Feature |  | Campaign Mgmt | API - Update Campaign. Not available for Campaigns in progress and closed
| New | New Feature |  | Campaign Mgmt | API - Update Campaign lines. Not available for Campaigns in progress and closed
| New | New Feature |  | Campaign Mgmt | API - Cancel Campaign (not applicable for in-progress and closed)
| New | New Feature |  | Campaign Mgmt | API - Close Campaign (not applicable for in-progress and closed)
| New | New Feature |  | Campaign Mgmt | When the campaign is in progress, No further changes should be allowed to be made in the campaign other than the call results. Also, the time-stamp of each campaign when started and completed should be available for reporting
| New | New Feature |  | Campaign Mgmt | When the camapaign gets completed, a notification should be sent to the requestor on the status
14 | TDEB-33 | Task |  | Architecture | Application and Deployment architecture - Arrive at the optimum sizing and also finalize the infra components
15 | TDEB-34 | Task |  | Architecture | Architecture diagram | [5 empty] | vinod, anand | In-progress
16 | TDEB-35 | Task |  | Architecture | Identify OAuth node package and do quick poc whether its fit for purpose
17 | TDEB-31 |  |  | Call Scheduler | Campaign Start: Call Distribution
18 | New |  |  | Call Scheduler | Analysis and Design of Call distribution |  |  |  | 2019-06-24 | 2019-07-03 | raj,anand,philip,karthik | In-progress
19 | New |  |  | Call Scheduler | Code distribution algorithm |  |  |  | 2019-07-04 | 2019-07-11 | parthiban
20 | New |  |  | Call Scheduler | Review of distribution algorithm
21 | New |  |  | Call Scheduler | Develop code to pick data from campaign lines and populate batch table | [8 empty] | 250
22 | New |  |  | Call Scheduler | Develop code to process data from Batch and update campaigns/lines |  |  |  | 2019-07-05 |  |  |  |  | 36000
24 | TDEB-13 |  |  | Call Scheduler | Talkdesk Campaign Services | [8 empty] | 3600
25 | New |  |  | Call Scheduler | Integrate scheduler, Presence and call distribution services | [8 empty] | 14.5 call in agent
26 | TDEB-32 |  |  | Call Scheduler | Agent Presence Logic
27 | New |  |  | Call Scheduler | Analysis of Presence API
28 | New |  |  | Call Scheduler | Create Code get all agents status and store in db
29 | New |  |  | Call Scheduler | Create code get aggregation of available status of agent
30 | New |  |  | Call Scheduler | Create api to read the no of agents available status
31 | TDEB-1 |  |  | Campaign Mgmt- UI | Utilize the Talkdesk Cobalt UI Framework with the Talkdesk EB App.
32 | TDEB-21 |  |  | Campaign Mgmt- UI | Edit Campaign Line Page for Cobalt | [6 empty] | Review
33 | TDEB-20 |  |  | Campaign Mgmt- UI | Edit Campaign Page for Cobalt | [6 empty] | Review
34 | TDEB-19 |  |  | Campaign Mgmt- UI | Campaign Line Page for Cobalt | [6 empty] | Review
35 | TDEB-18 |  |  | Campaign Mgmt- UI | Campaign Page for Cobalt | [6 empty] | Review
36 | TDEB-17 |  |  | Campaign Mgmt- UI | Convert Campaign Dashboard for Cobalt | [6 empty] | Review
37 | TDEB-16 |  |  | Campaign Mgmt- UI | Implement Talkdesk Dock with Drawer
38 | TDEB-11 |  |  | Campaign Mgmt- UI | The Process for Creating and Maintaining Campaigns
39 | TDEB-23 |  |  | Campaign Mgmt- UI | Edit Talkdesk Campaign Lines
40 | TDEB-22 |  |  | Campaign Mgmt- UI | Edit a Talkdesk Campaign
41 | TDEB-10 |  |  | Campaign Mgmt - UI | Create Talkdesk Campaign Lines
42 | TDEB-9 |  |  | Campaign Mgmt- UI | Create a Talkdesk Campaign
43 | TDEB-8 |  |  | Campaign Mgmt | Ability to Mass Import Campaign Lines Using a CSV File
44 |  |  |  | Campaign Management | As a user I would like buttons to control a campaign
45 | TDEB-27 |  |  | Camapaign Management | Campaign Pause Service
46 | TDEB-26 |  |  | Camapaign Managmnt | Campaign Stop Service
47 | TDEB-25 |  |  | Camapaign Managtmtnt | Campaign Start Service
48 | New |  |  | Campaign Management | Add tenant_id to all tables and refer in GUI
49 | TDEB-15 |  |  | User Administration | OAuth 2 for Partner and Third Party Integrations
50 | TDEB-28 |  |  | User Administration | As a Partner, I would like to request for a Client ID and Secret
51 | TDEB-30 |  |  | User Administration | As a Partner, I should be able to use a refresh token to request a new access token if the one currently in use expires
52 | TDEB-29 |  |  | User Administration | As a Partner, I should be able to request an access token using my Client ID and Secret
53 | New |  |  | Testing | Functional Integration Testing
54 | New |  |  | Testing | Performance Testing
55
56
57
58
59
60
61
62

## Sprint
| Start Date | End Date
Sprint 0
Sprint 1
Sprint 2
Sprint 3
Sprint 4